## Rekap
SUMMARY OF INVOICE
PROVINCIAL MANAGEMENT ADVISORY CONSULTANT (PMAC) | [7 empty] | No. Invoice | :2 (Dua)
TO THE PROVINCIAL PROJECT MANAGEMENT UNIT (PPMU) | [7 empty] | Periode | :1 Desember 2009 - 31 Januari 2010
PROVINCE OF CENTRAL SULAWESI (PACKAGE C-15) | [7 empty] | Contract | :No. KU.08.08/AM/14/2009 Tanggal 27 August 2009
[8 empty] | Memorandum No. 1 | :Tanggal 16 September 2009
[8 empty] | Memorandum No. 2 | :Tanggal 16 Desember 2009
NO. | DESCRIPTION | CONRACT |  | INVOICE | [5 empty] | UP TO THIS |  | REMAIN CONTRACT
|  |  |  | PREVIOUS | BOBOT | BIMONTLY NO.2 |  | THIS INVOICE | BOBOT | INVOICE | BOBOT
|  | Rp. | BOBOT (%) |  | (%) | DES'09 | JAN'10 |  | (%) |  | (%)
1 | REMUNERATION | 6724800000 | 57.118 | 373600000 | 3.1732 | 159300000 | 159300000 | 318600000 | 2.7061 | 692200000 | 5.8793 | 6032600000
2 | REIMBURSABLE EXPENSES | 5048725000 | 42.882 | 567650000 | 4.8214 | 37350000 | 35500000 | 72850000 | 0.61876 | 640500000 | 5.4402 | 4408225000
| TOTAL | 11773525000 | 100 | 941250000 | 7.9946 | 196650000 | 194800000 | 391450000 | 3.3248 | 1332700000 | 11.3195 | 10440825000
| Repayment of Advance Payment | 1177352500 |  | 196225500 |  |  |  | 196225500 |  | 392451000 |  | 784901500
| GRAND TOTAL | 10596172500 |  | 745024500 |  |  |  | 195224500 |  | 940249000 |  | 9655923500
| VAT 10% paid by Government (DGHS) or SPM Nihil | 1059617250 |  | 74502450 |  |  |  | 19522450 |  | 94024900 |  | 965592350
| Pejabat Pembuat Komitmen | [8 empty] | Jakarta, 31 Januari 2010
| Satuan Kerja Pengembangan Kinerja | [8 empty] | PT. PERENTJANA DJAJA
Pengelolaan Air Minum Sulawesi Tengah
| ISTIADJI, ST | [8 empty] | Ir. H. Bambang H Wikanta, MM, MT
| NIP. 195510301990031001 | [8 empty] | Precident Director

## Personil
PROVINCIAL MANAGEMENT ADVISORY CONSULTANT (PMAC) | [14 empty] | No. Invoice | :2 (Dua)
TO THE PROVINCIAL PROJECT MANAGEMENT UNIT (PPMU) | [14 empty] | Periode | :1 Desember 2009 - 31 Januari 2010
PROVINCE OF CENTRAL SULAWESI (PACKAGE C-15) | [14 empty] | Contract No | :No. KU.08.08/AM/14/2009 Tanggal 27 August 2009
[15 empty] | Memorandum No. 1 | :Tanggal 16 September 2009
[15 empty] | Memorandum No. 2 | :Tanggal 16 Desember 2009
NO. | NAME |  | CONTRACT |  |  |  | PREVIOUS |  |  | THIS INVOICE | [6 empty] | UP TO HIS INVOICE |  |  | REMAIN
|  | POSITION | MM | Billing Rate | Amount | Bobot | MM | Amount | Bobot | Man-Month |  |  | Sub Total |  |  |  | MM | Amount | Bobot (%) | MM | Amount
|  |  |  | (IDR) | (IDR) | (%) |  | (IDR) | (%) | Des'09 | Jan'10 | Total | Des'09 | Jan'10 | Total | Bobot (%) |  | (IDR) |  |  | (IDR)
A. | REMUNERATION | REMUNERATION
A.I | PROFESSIONAL STAFF | PROFESSIONAL STAFF
1 | Asep Sulaeman | Team Leader | 36 |  | 0 | 4.2808 | 2 | 0 | 0.23782 | 1 | 1 | 2 | 0 | 0 | 0 | 0.23782 | 4 | 0 | 0.47564 | 32 | 0
DONGGALA
2 | Tahir Dalango | Water Supply Eng. & Communal Sanitation Construction Spec. (WSE-CSS) | 36 |  | 0 | 2.8131 | 2 | 0 | 0.15628 | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 4 | 0 | 0.31257 | 32 | 0
3 | Valentina Paranten | District Health & Hygiene Specialist (HHS) | 36 |  | 0 | 2.8131 | 2 | 0 | 0.15628 | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 4 | 0 | 0.31257 | 32 | 0
TOJO UNA UNA
4 | Adi Mardjani | Water Supply Eng. & Communal Sanitation Construction Spec. (WSE-CSS) | 36 |  | 0 | 2.8131 | 2 | 0 | 0.15628 | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 4 | 0 | 0.31257 | 32 | 0
5 | Muh. Ali Bahri | District Health & Hygiene Specialist (HHS) | 36 |  | 0 | 2.8131 | 2 | 0 | 0.15628 | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 4 | 0 | 0.31257 | 32 | 0
POSO
6 | Sentot Budiyanto | Water Supply Eng. & Communal Sanitation Construction Spec. (WSE-CSS) | 36 |  | 0 | 2.8131 | 2 | 0 | 0.15628 | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 4 | 0 | 0.31257 | 32 | 0
7 | Abdulah Pamalo | District Health & Hygiene Specialist (HHS) | 36 |  | 0 | 2.8131 | 2 | 0 | 0.15628 | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 4 | 0 | 0.31257 | 32 | 0
BUOL
8 | Luluk Budijono | Water Supply Eng. & Communal Sanitation Construction Spec. (WSE-CSS) | 36 |  | 0 | 2.8131 | 2 | 0 | 0.15628 | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 4 | 0 | 0.31257 | 32 | 0
9 | Theresia Oktaviani | District Health & Hygiene Specialist (HHS) | 36 |  | 0 | 2.8131 | 2 | 0 | 0.15628 | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 4 | 0 | 0.31257 | 32 | 0
MOROWALI
10 | Hesti Damayanti | Water Supply Eng. & Communal Sanitation Construction Spec. (WSE-CSS) | 36 |  | 0 | 2.8131 | 2 | 0 | 0.15628 | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 4 | 0 | 0.31257 | 32 | 0
11 | Kahardiansyah | District Health & Hygiene Specialist (HHS) | 36 |  | 0 | 2.8131 | 2 | 0 | 0.15628 | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 4 | 0 | 0.31257 | 32 | 0
BANGGAI KEPULAUAN
12 | Sixsanto Esa | Water Supply Eng. & Communal Sanitation Construction Spec. (WSE-CSS) | 36 |  | 0 | 2.8131 | 2 | 0 | 0.15628 | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 4 | 0 | 0.31257 | 32 | 0
13 | Muhamad Iqsan | District Health & Hygiene Specialist (HHS) | 36 |  | 0 | 2.8131 | 2 | 0 | 0.15628 | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 4 | 0 | 0.31257 | 32 | 0
PARIGI MOUTONG
14 | Salida Arianti | Water Supply Eng. & Communal Sanitation Construction Spec. (WSE-CSS) | 36 |  | 0 | 2.8131 | 2 | 0 | 0.15628 | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 4 | 0 | 0.31257 | 32 | 0
15 | Sarinah | District Health & Hygiene Specialist (HHS) | 36 |  | 0 | 2.8131 | 2 | 0 | 0.15628 | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 4 | 0 | 0.31257 | 32 | 0
[5 empty] | 5140800000 | 43.6641 |  | 285600000 | 2.4258 |  |  |  | 142800000 | 142800000 | 285600000 | 2.4258 |  | 571200000 | 4.8516 |  | 4569600000
A.II | SUPPORTINS STAFF | SUPPORTINS STAFF
| PROVINCE | PROVINCE
1 | Abdul Rasyid | Data Manag / Comp Operator | 36 |  | 0 | 0.76443 | 2 | 0 | 0.042468 | 1 | 1 | 2 | 0 | 0 | 0 | 0.042468 | 4 | 0 | 0.084936 | 32 | 0
2 | Suryanto | Administration | 36 |  | 0 | 0.61154 | 2 | 0 | 0.033975 | 1 | 1 | 2 | 0 | 0 | 0 | 0.033975 | 4 | 0 | 0.067949 | 32 | 0
3 |  | Driver | 36 |  | 0 | 0.30577 | 2 | 0 | 0.016987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0.016987 | 34 | 0
| DISTRICT | DISTRICT
1 | Ricki Susanto | Administration / Computer Operator | 36 |  | 0 | 0.61154 | 2 | 0 | 0.033975 | 1 | 1 | 2 | 0 | 0 | 0 | 0.033975 | 4 | 0 | 0.067949 | 32 | 0
2 | Ibnu Hajar Kalumu | Administration / Computer Operator | 36 |  | 0 | 0.61154 | 2 | 0 | 0.033975 | 1 | 1 | 2 | 0 | 0 | 0 | 0.033975 | 4 | 0 | 0.067949 | 32 | 0
3 |  | Administration / Computer Operator | 36 |  | 0 | 0.61154 | 2 | 0 | 0.033975 |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0.033975 | 34 | 0
4 | Herlina Muslimin | Administration / Computer Operator | 36 |  | 0 | 0.61154 | 2 | 0 | 0.033975 | 1 | 1 | 2 | 0 | 0 | 0 | 0.033975 | 4 | 0 | 0.067949 | 32 | 0
5 | Sri Wahyuni | Administration / Computer Operator | 36 |  | 0 | 0.61154 | 2 | 0 | 0.033975 | 1 | 1 | 2 | 0 | 0 | 0 | 0.033975 | 4 | 0 | 0.067949 | 32 | 0
6 | Yuliyanati | Administration / Computer Operator | 36 |  | 0 | 0.61154 | 2 | 0 | 0.033975 | 1 | 1 | 2 | 0 | 0 | 0 | 0.033975 | 4 | 0 | 0.067949 | 32 | 0
7 | Deddy Kwarto | Administration / Computer Operator | 36 |  | 0 | 0.61154 | 2 | 0 | 0.033975 | 1 | 1 | 2 | 0 | 0 | 0 | 0.033975 | 4 | 0 | 0.067949 | 32 | 0
8 |  | Draftman | 36 |  | 0 | 0.76443 | 2 | 0 | 0.042468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0.042468 | 34 | 0
9 |  | Draftman | 36 |  | 0 | 0.76443 | 2 | 0 | 0.042468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0.042468 | 34 | 0
10 |  | Draftman | 36 |  | 0 | 0.76443 | 2 | 0 | 0.042468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0.042468 | 34 | 0
11 |  | Draftman | 36 |  | 0 | 0.76443 | 2 | 0 | 0.042468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0.042468 | 34 | 0
12 |  | Draftman | 36 |  | 0 | 0.76443 | 2 | 0 | 0.042468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0.042468 | 34 | 0
13 |  | Draftman | 36 |  | 0 | 0.76443 | 2 | 0 | 0.042468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0.042468 | 34 | 0
14 |  | Draftman | 36 |  | 0 | 0.76443 | 2 | 0 | 0.042468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0.042468 | 34 | 0
15 |  | Driver | 36 |  | 0 | 0.30577 | 2 | 0 | 0.016987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0.016987 | 34 | 0
16 |  | Driver | 36 |  | 0 | 0.30577 | 2 | 0 | 0.016987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0.016987 | 34 | 0
17 |  | Driver | 36 |  | 0 | 0.30577 | 2 | 0 | 0.016987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0.016987 | 34 | 0
18 |  | Driver | 36 |  | 0 | 0.30577 | 2 | 0 | 0.016987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0.016987 | 34 | 0
19 |  | Driver | 36 |  | 0 | 0.30577 | 2 | 0 | 0.016987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0.016987 | 34 | 0
20 |  | Driver | 36 |  | 0 | 0.30577 | 2 | 0 | 0.016987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0.016987 | 34 | 0
21 |  | Driver | 36 |  | 0 | 0.30577 | 2 | 0 | 0.016987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0.016987 | 34 | 0
[5 empty] | 1584000000 | 13.4539 |  | 88000000 | 0.74744 |  |  |  | 16500000 | 16500000 | 33000000 | 0.28029 |  | 121000000 | 1.0277 |  | 1463000000
[5 empty] | 6724800000 | 57.118 |  | 373600000 | 3.1732 |  |  |  | 159300000 | 159300000 | 318600000 | 2.7061 |  | 692200000 | 5.8793 |  | 6032600000

## Non Personil
PROVINCIAL MANAGEMENT ADVISORY CONSULTANT (PMAC) | [13 empty] | No. Invoice | :2 (Dua)
TO THE PROVINCIAL PROJECT MANAGEMENT UNIT (PPMU) | [13 empty] | Periode | :1 Desember 2009 - 31 Januari 2010
PROVINCE OF CENTRAL SULAWESI (PACKAGE C-15) | [13 empty] | Contract | :No. KU.08.08/AM/14/2009 Tanggal 27 August 2009
[14 empty] | Memorandum No. 1 | :Tanggal 16 September 2009
B. REIMBURSABLE EXPENSES | [13 empty] | Memorandum No. 2 | :Tanggal 16 Desember 2009
NO. | DESCRIPTION | CONTRACT |  |  |  | PREVIOUS |  |  | THIS INVOICE | [6 empty] | UP TO HIS INVOICE |  |  | REMAIN
|  | MM | Billing Rate | Amount | Bobot | MM | Amount | Bobot | Man-Month |  |  | Sub Total |  |  |  | MM | Amount | Bobot (%) | MM | Amount
|  |  | Rp | Rp | (%) |  | Rp | (%) | Des'09 | Jan'10 | Total | Des'09 | Jan'10 | Total | Bobot (%) |  | Rp |  |  | Rp
B.I | MOBILIZATION / DEMOBILIZATION
1 | Provincial Team Leader (Jkt - Palu) | 1 | 3200000 | 3200000 | 0.02718 | 0.5 | 1600000 | 0.01359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1600000 | 0.01359 | 0.5 | 1600000
2 | Water Supply Eng/ (WSE-CSS) (Jkt - Palu - District) | 7 | 3700000 | 25900000 | 0.21999 | 0.5 | 1850000 | 0.015713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1850000 | 0.015713 | 6.5 | 24050000
3 | District Health & Hygiene Specialist (HHS) (Jkt - Palu - District) | 7 | 3700000 | 25900000 | 0.21999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 25900000
| Sub Total B.I |  |  | 55000000 | 0.46715 |  | 3450000 | 0.029303 |  |  |  | 0 | 0 | 0 | 0 |  | 3450000 | 0.029303 |  | 51550000
1 | Provincial Team Leader :
| a. Transportation Province to Jakarta (2 trips/year) | 6 | 3200000 | 19200000 | 0.16308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 19200000
| b. Transportation Province to District (2 trips/year/district) = (3 years) | 42 | 500000 | 21000000 | 0.17837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 21000000
2 | Water Supply Eng/ (WSE-CSS) :
| a. Transportation District to Jakarta (1 trip/year) | 21 | 3700000 | 77700000 | 0.65996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 77700000
| b. Transportation District to Province (4 trips/year) = (3 years) | 84 | 500000 | 42000000 | 0.35673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 42000000
3 | District Health & Hygiene Specialist (HHS) :
| a. Transportation District to Jakarta (1 trip/year) | 21 | 3700000 | 77700000 | 0.65996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 77700000
| b. Transportation District to Province (4 trips/year) = (3 years) | 84 | 500000 | 42000000 | 0.35673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 42000000
| Sub Total B.III |  |  | 279600000 | 2.3748 |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 279600000
B.II | CAR RENTAL
1 | Provincial :
| Car Rental and O & M (1 unit x 36 months) | 36 | 7000000 | 252000000 | 2.1404 | 2 | 14000000 | 0.11891 |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 14000000 | 0.11891 | 34 | 238000000
2 | Districts :
| Car Rental and O & M (7 unit x 36 months) | 252 | 7000000 | 1764000000 | 14.9828 | 14 | 98000000 | 0.83238 |  |  | 0 | 0 | 0 | 0 | 0 | 14 | 98000000 | 0.83238 | 238 | 1666000000
| Sub Total B.V |  |  | 2016000000 | 17.1232 |  | 112000000 | 0.95129 |  |  |  | 0 | 0 | 0 | 0 | 16 | 112000000 | 0.95129 |  | 1904000000
B.III | OUT OF STATION ALLOWANCE (OSA)
1 | Provincial Team Leader :
| a. OSA to Jakarta (2 trips/year @ 2 days) | 12 | 700000 | 8400000 | 0.071347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 8400000
| b. OSA to District (2 trips/year/district @ 2 days) | 84 | 500000 | 42000000 | 0.35673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 42000000
2 | Water Supply Eng/ (WSE-CSS) :
| a. OSA to Jkt (1 trip/year @ 2 days) | 84 | 700000 | 58800000 | 0.49943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 58800000
| b. OSA to Province (4 trips/year @ 3 days) | 252 | 500000 | 126000000 | 1.0702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 126000000
| c. OSA District to Villages (1 trip/month @ 14 days) | 3528 | 50000 | 176400000 | 1.4983 | 0 | 0 | 0 | 53 | 63 | 116 | 2650000 | 3150000 | 5800000 | 0.049263 | 116 | 5800000 | 0.049263 | 3412 | 170600000
3 | District Health & Hygiene Specialist (HHS) :
| a. OSA to Jkt (1 trip/year @ 2 days) | 84 | 700000 | 58800000 | 0.49943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 58800000
| b. OSA to Province (4 trips/year @ 3 days) | 252 | 500000 | 126000000 | 1.0702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 126000000
| c. OSA District to Villages (1 trip/month @ 14 days) | 3528 | 50000 | 176400000 | 1.4983 | 0 | 0 | 0 | 48 | 46 | 94 | 2400000 | 2300000 | 4700000 | 0.03992 | 94 | 4700000 | 0.03992 | 3434 | 171700000
| Sub Total B.IV |  |  | 772800000 | 6.5639 |  | 0 | 0 |  |  |  | 5050000 | 5450000 | 10500000 | 0.089183 |  | 10500000 | 0.089183 |  | 762300000
B.IV | Housing Allowance
1 | Provincial Team Leader | 36 | 800000 | 28800000 | 0.24462 | 2 | 1600000 | 0.01359 | 1 | 1 | 2 | 800000 | 800000 | 1600000 | 0.01359 | 4 | 3200000 | 0.02718 | 32 | 25600000
2 | Water Supply Eng/ (WSE-CSS) | 252 | 600000 | 151200000 | 1.2842 | 14 | 8400000 | 0.071347 | 7 | 7 | 14 | 4200000 | 4200000 | 8400000 | 0.071347 | 28 | 16800000 | 0.14269 | 224 | 134400000
3 | District Health & Hygiene Specialist (HHS) | 252 | 600000 | 151200000 | 1.2842 | 14 | 8400000 | 0.071347 | 7 | 7 | 14 | 4200000 | 4200000 | 8400000 | 0.071347 | 28 | 16800000 | 0.14269 | 224 | 134400000
| Sub Total B.II |  |  | 331200000 | 2.8131 |  | 18400000 | 0.15628 |  |  |  | 9200000 | 9200000 | 18400000 | 0.15628 |  | 36800000 | 0.31257 |  | 294400000
B.V | TELECOMMUNICATION
1 | Provincial Office (Phone, Facs, Email, Post, Internet etc) | 36 | 750000 | 27000000 | 0.22933 | 2 | 1500000 | 0.01274 | 1 | 1 | 2 | 750000 | 750000 | 1500000 | 0.01274 | 4 | 3000000 | 0.025481 | 32 | 24000000
2 | District Office (Phone, Facs, Email, Post Internet etc) (7 Dist. x 36 months) | 252 | 300000 | 75600000 | 0.64212 | 14 | 4200000 | 0.035673 | 7 | 7 | 14 | 2100000 | 2100000 | 4200000 | 0.035673 | 28 | 8400000 | 0.071347 | 224 | 67200000
| Sub Total B.VIII |  |  | 102600000 | 0.87145 |  | 5700000 | 0.048414 |  |  |  | 2850000 | 2850000 | 5700000 | 0.048414 |  | 11400000 | 0.096827 |  | 91200000
B.VI | OFFICE EQUIPMENTS
1 | Provincial Office :
| a. Computer (rental) 2 unit/month | 72 | 700000 | 50400000 | 0.42808 | 4 | 2800000 | 0.023782 | 2 | 2 | 4 | 1400000 | 1400000 | 2800000 | 0.023782 | 8 | 5600000 | 0.047564 | 64 | 44800000
| b. Printer (rental) 1unit/month | 36 | 350000 | 12600000 | 0.10702 | 2 | 700000 | 0.0059455 | 1 | 1 | 2 | 350000 | 350000 | 700000 | 0.0059455 | 4 | 1400000 | 0.011891 | 32 | 11200000
2 | District Office (7 Offices) :
| a. Computer (rental) 2 unit/district/month | 504 | 750000 | 378000000 | 3.2106 | 14 | 10500000 | 0.089183 | 7 | 7 | 14 | 5250000 | 5250000 | 10500000 | 0.089183 | 28 | 21000000 | 0.17837 | 476 | 357000000
| b. Printer (rental) 1 unit/month | 252 | 350000 | 88200000 | 0.74914 | 14 | 4900000 | 0.041619 | 7 | 7 | 14 | 2450000 | 2450000 | 4900000 | 0.041619 | 28 | 9800000 | 0.083238 | 224 | 78400000
| c. Digital Camera (rental) 1 unit/month/district | 252 | 200000 | 50400000 | 0.42808 | 14 | 2800000 | 0.023782 | 7 | 7 | 14 | 1400000 | 1400000 | 2800000 | 0.023782 | 28 | 5600000 | 0.047564 | 224 | 44800000
| Sub Total B.VI |  |  | 579600000 | 4.9229 |  | 21700000 | 0.18431 |  |  |  | 10850000 | 10850000 | 21700000 | 0.18431 |  | 43400000 | 0.36862 |  | 536200000
B.VII | OFFICE COST
1 | Provincial Office :
| a. Office Supply | 36 | 400000 | 14400000 | 0.12231 | 2 | 800000 | 0.0067949 | 1 | 1 | 2 | 400000 | 400000 | 800000 | 0.0067949 | 4 | 1600000 | 0.01359 | 32 | 12800000
| b. Computer/Printer Supply | 36 | 400000 | 14400000 | 0.12231 | 2 | 800000 | 0.0067949 | 1 | 1 | 2 | 400000 | 400000 | 800000 | 0.0067949 | 4 | 1600000 | 0.01359 | 32 | 12800000
2 | District Office (7 Offices) :
| a. Office Supply | 252 | 400000 | 100800000 | 0.85616 | 14 | 5600000 | 0.047564 | 7 | 7 | 14 | 2800000 | 2800000 | 5600000 | 0.047564 | 28 | 11200000 | 0.095129 | 224 | 89600000
| b. Computer/Printer Supply | 252 | 400000 | 100800000 | 0.85616 | 14 | 5600000 | 0.047564 | 7 | 7 | 14 | 2800000 | 2800000 | 5600000 | 0.047564 | 28 | 11200000 | 0.095129 | 224 | 89600000
| c. Survey Equipments (7 X 12) | 84 | 500000 | 42000000 | 0.35673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 42000000
| Sub Total B.VII |  |  | 272400000 | 2.3137 |  | 12800000 | 0.10872 |  |  |  | 6400000 | 6400000 | 12800000 | 0.10872 |  | 25600000 | 0.21744 |  | 246800000
B.VIII | REPORTS
1 | Inception Report (15 copies)/district | 15 | 50000 | 750000 | 0.0063702 | 0 | 0 | 0 | 15 | 0 | 15 | 750000 | 0 | 750000 | 0.0063702 | 15 | 750000 | 0.0063702 | 0 | 0
2 | Monthly Report (15 copies/month)/district | 540 | 50000 | 27000000 | 0.22933 | 0 | 0 | 0 | 45 | 15 | 60 | 2250000 | 750000 | 3000000 | 0.025481 | 60 | 3000000 | 0.025481 | 480 | 24000000
3 | Quarterly Report (15 copies/3 months)/district | 180 | 50000 | 9000000 | 0.076443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 9000000
4 | Annual Report (15 copies/year)/district | 45 | 75000 | 3375000 | 0.028666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 3375000
5 | Special Report (5 copies/years)/district | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
6 | Years Report | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
7 | Draft Final Report (15 copies)/district | 15 | 100000 | 1500000 | 0.01274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1500000
8 | Prov. Gov ICR Report | 45 | 100000 | 4500000 | 0.038221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 4500000
9 | Final Report (15 copies)/district | 15 | 150000 | 2250000 | 0.019111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2250000
10 | MIS Input (5 copies)/6 month/district | 15 | 50000 | 750000 | 0.0063702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 750000
| Sub Total B.IX |  |  | 49125000 | 0.41725 |  | 0 | 0 |  |  |  | 3000000 | 750000 | 3750000 | 0.031851 |  | 3750000 | 0.031851 |  | 45375000
B.IX | OFFICE RENTAL & FURNITURE AND O & M
1 | Province Office Rental (1 unit x 36 months) | 3 | 28800000 | 86400000 | 0.73385 | 2 | 57600000 | 0.48923 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 57600000 | 0.48923 | 1 | 28800000
2 | District Office Rental (7 unit x 36 months) | 252 | 2000000 | 504000000 | 4.2808 | 168 | 336000000 | 2.8539 |  |  | 0 | 0 | 0 | 0 | 0 | 168 | 336000000 | 2.8539 | 84 | 168000000
| Sub Total B.X |  |  | 590400000 | 5.0146 |  | 393600000 | 3.3431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 393600000 | 3.3431 |  | 196800000
| TOTAL REIMBURSABLE EXPENSES |  |  | 5048725000 | 42.882 |  | 567650000 | 4.8214 |  |  |  | 37350000 | 35500000 | 72850000 | 0.61876 |  | 640500000 | 5.4402 |  | 4408225000