## Rekap
SUMMARY OF INVOICE
PROVINCIAL MANAGEMENT ADVISORY CONSULTANT (PMAC) | [6 empty] | No. Invoice | :1 (Satu)
TO THE PROVINCIAL PROJECT MANAGEMENT UNIT (PPMU) | [6 empty] | Periode | :1 October 2009 - 30 November 2009
PROVINCE OF CENTRAL SULAWESI (PACKAGE C-15) | [6 empty] | Contract | :No. KU.08.08/AM/14/2009 Tanggal 27 August 2009
[7 empty] | Memorandum | :Tanggal 16 September 2009
NO. | DESCRIPTION | CONRACT |  | INVOICE |  |  |  |  | UP TO THIS INVOICE | REMAIN CONTRACT
|  |  |  | PREVIOUS | BIMONTLY NO.1 |  | THIS INVOICE | BOBOT
|  | Rp. | BOBOT (%) |  | OCT'09 | NOV'09 |  | (%)
1 | REMUNERATION | 6724800000 | 57.118 | 0 | 186800000 | 186800000 | 373600000 | 3.1732 | 373600000 | 6351200000
2 | REIMBURSABLE EXPENSES | 5048725000 | 42.882 | 0 | 482350000 | 85300000 | 567650000 | 4.8214 | 567650000 | 4481075000
| TOTAL | 11773525000 | 100 | 0 | 669150000 | 272100000 | 941250000 | 7.9946 | 941250000 | 10832275000
| Repayment of Advance Payment | 1177352500 |  | 0 |  |  | 196225500 |  | 196225500 | 981127000
| GRAND TOTAL | 10596172500 |  | 0 |  |  | 745024500 |  | 745024500 | 9851148000
| VAT 10% paid by Government (DGHS) or SPM Nihil | 1059617250 |  | 0 |  |  | 74502450 |  | 74502450 | 985114800
| Pejabat Pembuat Komitmen | [7 empty] | Jakarta, 10 Desember 2009
| Satuan Kerja Pengembangan Kinerja | [7 empty] | PT. PERENTJANA DJAJA
Pengelolaan Air Minum Sulawesi Tengah
| ISTIAJI, ST | [7 empty] | Ir. H. Bambang H Wikanta, MM, MT
| NIP. 110 044 047 | [7 empty] | Precident Director

## Personil
PROVINCIAL MANAGEMENT ADVISORY CONSULTANT (PMAC) | [12 empty] | No. Invoice | :1 (Satu)
TO THE PROVINCIAL PROJECT MANAGEMENT UNIT (PPMU) | [12 empty] | Periode | :1 October 2009 - 30 November 2009
PROVINCE OF CENTRAL SULAWESI (PACKAGE C-15) | [12 empty] | Contract No | :No. KU.08.08/AM/14/2009 Tanggal 27 August 2009
[13 empty] | Memorandum | :Tanggal 16 September 2009
NO. | NAME |  | CONTRACT |  |  |  | PREVIOUS |  | THIS INVOICE | [6 empty] | UP TO HIS INVOICE |  | REMAIN
|  | POSITION | MM | Billing Rate | Amount | Bobot | MM | Amount | Man-Month |  |  | Sub Total |  |  |  | MM | Amount | MM | Amount
|  |  |  | (IDR) | (IDR) | (%) |  | (IDR) | Oct | Nov | Total | Oct | Nov | Total | Bobot (%) |  | (IDR) |  | (IDR)
A. | REMUNERATION | REMUNERATION
A.I | PROFESSIONAL STAFF | PROFESSIONAL STAFF
1 | Asep Sulaeman | Team Leader | 36 |  |  | 4.2808 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.23782 | 2 | 0 | 34 | 0
DONGGALA
2 | Tahir Dalango | Water Supply Eng. & Communal Sanitation Construction Spec. (WSE-CSS) | 36 |  |  | 2.8131 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 2 | 0 | 34 | 0
3 | Valentina Paranten | District Health & Hygiene Specialist (HHS) | 36 |  |  | 2.8131 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 2 | 0 | 34 | 0
TOJO UNA UNA
4 | Adi Mardjani | Water Supply Eng. & Communal Sanitation Construction Spec. (WSE-CSS) | 36 |  |  | 2.8131 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 2 | 0 | 34 | 0
5 | Muh. Ali Bahri | District Health & Hygiene Specialist (HHS) | 36 |  |  | 2.8131 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 2 | 0 | 34 | 0
POSO
6 | Sentot Budiyanto | Water Supply Eng. & Communal Sanitation Construction Spec. (WSE-CSS) | 36 |  |  | 2.8131 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 2 | 0 | 34 | 0
7 | Abdulah Pamalo | District Health & Hygiene Specialist (HHS) | 36 |  |  | 2.8131 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 2 | 0 | 34 | 0
BUOL
8 | Luluk Budijono | Water Supply Eng. & Communal Sanitation Construction Spec. (WSE-CSS) | 36 |  |  | 2.8131 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 2 | 0 | 34 | 0
9 | Theresia Oktaviani | District Health & Hygiene Specialist (HHS) | 36 |  |  | 2.8131 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 2 | 0 | 34 | 0
MOROWALI
10 | Hesti Damayanti | Water Supply Eng. & Communal Sanitation Construction Spec. (WSE-CSS) | 36 |  |  | 2.8131 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 2 | 0 | 34 | 0
11 | Kahardiansyah | District Health & Hygiene Specialist (HHS) | 36 |  |  | 2.8131 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 2 | 0 | 34 | 0
BANGGAI KEPULAUAN
12 | Sixsanto Esa | Water Supply Eng. & Communal Sanitation Construction Spec. (WSE-CSS) | 36 |  |  | 2.8131 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 2 | 0 | 34 | 0
13 | Muhamad Iqsan | District Health & Hygiene Specialist (HHS) | 36 |  |  | 2.8131 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 2 | 0 | 34 | 0
PARIGI MOUTONG
14 | Salida Arianti | Water Supply Eng. & Communal Sanitation Construction Spec. (WSE-CSS) | 36 |  |  | 2.8131 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 2 | 0 | 34 | 0
15 | Sarinah | District Health & Hygiene Specialist (HHS) | 36 |  |  | 2.8131 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.15628 | 2 | 0 | 34 | 0
[5 empty] | 5140800000 | 43.6641 |  | 0 |  |  |  | 142800000 | 142800000 | 285600000 | 2.4258 |  | 285600000 |  | 4855200000
A.II | SUPPORTINS STAFF | SUPPORTINS STAFF
| PROVINCE | PROVINCE
1 |  | Data Manag / Comp Operator | 36 |  |  | 0.76443 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.042468 | 2 | 0 | 34 | 0
2 |  | Administration | 36 |  |  | 0.61154 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.033975 | 2 | 0 | 34 | 0
3 |  | Driver | 36 |  |  | 0.30577 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.016987 | 2 | 0 | 34 | 0
| DISTRICT | DISTRICT
1 |  | Administration / Computer Operator | 36 |  |  | 0.61154 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.033975 | 2 | 0 | 34 | 0
2 |  | Administration / Computer Operator | 36 |  |  | 0.61154 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.033975 | 2 | 0 | 34 | 0
3 |  | Administration / Computer Operator | 36 |  |  | 0.61154 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.033975 | 2 | 0 | 34 | 0
4 |  | Administration / Computer Operator | 36 |  |  | 0.61154 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.033975 | 2 | 0 | 34 | 0
5 |  | Administration / Computer Operator | 36 |  |  | 0.61154 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.033975 | 2 | 0 | 34 | 0
6 |  | Administration / Computer Operator | 36 |  |  | 0.61154 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.033975 | 2 | 0 | 34 | 0
7 |  | Administration / Computer Operator | 36 |  |  | 0.61154 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.033975 | 2 | 0 | 34 | 0
8 |  | Draftman | 36 |  |  | 0.76443 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.042468 | 2 | 0 | 34 | 0
9 |  | Draftman | 36 |  |  | 0.76443 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.042468 | 2 | 0 | 34 | 0
10 |  | Draftman | 36 |  |  | 0.76443 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.042468 | 2 | 0 | 34 | 0
11 |  | Draftman | 36 |  |  | 0.76443 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.042468 | 2 | 0 | 34 | 0
12 |  | Draftman | 36 |  |  | 0.76443 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.042468 | 2 | 0 | 34 | 0
13 |  | Draftman | 36 |  |  | 0.76443 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.042468 | 2 | 0 | 34 | 0
14 |  | Draftman | 36 |  |  | 0.76443 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.042468 | 2 | 0 | 34 | 0
15 |  | Driver | 36 |  |  | 0.30577 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.016987 | 2 | 0 | 34 | 0
16 |  | Driver | 36 |  |  | 0.30577 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.016987 | 2 | 0 | 34 | 0
17 |  | Driver | 36 |  |  | 0.30577 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.016987 | 2 | 0 | 34 | 0
18 |  | Driver | 36 |  |  | 0.30577 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.016987 | 2 | 0 | 34 | 0
19 |  | Driver | 36 |  |  | 0.30577 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.016987 | 2 | 0 | 34 | 0
20 |  | Driver | 36 |  |  | 0.30577 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.016987 | 2 | 0 | 34 | 0
21 |  | Driver | 36 |  |  | 0.30577 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0.016987 | 2 | 0 | 34 | 0
[5 empty] | 1584000000 | 13.4539 |  | 0 |  |  |  | 44000000 | 44000000 | 88000000 | 0.74744 |  | 88000000 |  | 1496000000
[5 empty] | 6724800000 | 57.118 |  | 0 |  |  |  | 186800000 | 186800000 | 373600000 | 3.1732 |  | 373600000 |  | 6351200000

## Non Personil
PROVINCIAL MANAGEMENT ADVISORY CONSULTANT (PMAC) | [12 empty] | No. Invoice | :1 (Satu)
TO THE PROVINCIAL PROJECT MANAGEMENT UNIT (PPMU) | [12 empty] | Periode | :1 October 2009 - 30 November 2009
PROVINCE OF CENTRAL SULAWESI (PACKAGE C-15) | [12 empty] | Contract | :No. KU.08.08/AM/14/2009 Tanggal 27 August 2009
[13 empty] | Memorandum | :Tanggal 16 September 2009
B. REIMBURSABLE EXPENSES
NO. | DESCRIPTION | CONTRACT |  |  |  | PREVIOUS |  | THIS INVOICE | [6 empty] | UP TO HIS INVOICE |  | REMAIN
|  | MM | Billing Rate | Amount | Bobot | MM | Amount | Man-Month |  |  | Sub Total |  |  |  | MM | Amount | MM | Amount
|  |  | Rp | Rp | (%) |  | Rp | Oct | Nov | Total | Oct | Nov | Total | Bobot (%) |  | Rp |  | Rp
B.I | MOBILIZATION / DEMOBILIZATION
1 | Provincial Team Leader (Jkt - Palu) | 1 |  | 0 | 0.02718 |  | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0.01359 | 0.5 | 0 | 0.5 | 0
2 | Water Supply Eng/ (WSE-CSS) (Jkt - Palu - District) | 7 |  | 0 | 0.21999 |  | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0.015713 | 0.5 | 0 | 6.5 | 0
3 | District Health & Hygiene Specialist (HHS) (Jkt - Palu - District) | 7 |  | 0 | 0.21999 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0
| Sub Total B.I |  |  | 55000000 | 0.46715 |  | 0 |  |  |  | 3450000 | 0 | 3450000 | 0.029303 |  | 3450000 |  | 51550000
1 | Provincial Team Leader :
| a. Transportation Province to Jakarta (2 trips/year) | 6 |  | 0 | 0.16308 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0
| b. Transportation Province to District (2 trips/year/district) = (3 years) | 42 |  | 0 | 0.17837 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0
2 | Water Supply Eng/ (WSE-CSS) :
| a. Transportation District to Jakarta (1 trip/year) | 21 |  | 0 | 0.65996 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0
| b. Transportation District to Province (4 trips/year) = (3 years) | 84 |  | 0 | 0.35673 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 0
3 | District Health & Hygiene Specialist (HHS) :
| a. Transportation District to Jakarta (1 trip/year) | 21 |  | 0 | 0.65996 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0
| b. Transportation District to Province (4 trips/year) = (3 years) | 84 |  | 0 | 0.35673 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 0
| Sub Total B.III |  |  | 279600000 | 2.3748 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 279600000
B.II | CAR RENTAL
1 | Provincial :
| Car Rental and O & M (1 unit x 36 months) | 36 |  | 0 | 2.1404 |  | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0.11891 | 2 | 0 | 34 | 0
2 | Districts :
| Car Rental and O & M (7 unit x 36 months) | 252 |  | 0 | 14.9828 |  | 0 | 7 | 7 | 14 | 0 | 0 | 0 | 0.83238 | 14 | 0 | 238 | 0
| Sub Total B.V |  |  | 2016000000 | 17.1232 |  | 0 |  |  |  | 56000000 | 56000000 | 112000000 | 0.95129 | 16 | 112000000 |  | 1904000000
B.III | OUT OF STATION ALLOWANCE (OSA)
1 | Provincial Team Leader :
| a. OSA to Jakarta (2 trips/year @ 2 days) | 12 |  | 0 | 0.071347 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0
| b. OSA to District (2 trips/year/district @ 2 days) | 84 |  | 0 | 0.35673 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 0
2 | Water Supply Eng/ (WSE-CSS) :
| a. OSA to Jkt (1 trip/year @ 2 days) | 84 |  | 0 | 0.49943 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 0
| b. OSA to Province (4 trips/year @ 3 days) | 252 |  | 0 | 1.0702 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 0
| c. OSA District to Villages (1 trip/month @ 14 days) | 3528 |  | 0 | 1.4983 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3528 | 0
3 | District Health & Hygiene Specialist (HHS) :
| a. OSA to Jkt (1 trip/year @ 2 days) | 84 |  | 0 | 0.49943 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 0
| b. OSA to Province (4 trips/year @ 3 days) | 252 |  | 0 | 1.0702 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 0
| c. OSA District to Villages (1 trip/month @ 14 days) | 3528 |  | 0 | 1.4983 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3528 | 0
| Sub Total B.IV |  |  | 772800000 | 6.5639 |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  | 772800000
B.IV | Housing Allowance
1 | Provincial Team Leader | 36 |  | 0 | 0.24462 |  | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0.01359 | 2 | 0 | 34 | 0
2 | Water Supply Eng/ (WSE-CSS) | 252 |  | 0 | 1.2842 |  | 0 | 7 | 7 | 14 | 0 | 0 | 0 | 0.071347 | 14 | 0 | 238 | 0
3 | District Health & Hygiene Specialist (HHS) | 252 |  | 0 | 1.2842 |  | 0 | 7 | 7 | 14 | 0 | 0 | 0 | 0.071347 | 14 | 0 | 238 | 0
| Sub Total B.II |  |  | 331200000 | 2.8131 | [5 empty] | 9200000 | 9200000 | 18400000 | 0.15628 |  | 18400000 |  | 312800000
B.V | TELECOMMUNICATION
1 | Provincial Office (Phone, Facs, Email, Post, Internet etc) | 36 |  | 0 | 0.22933 |  | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0.01274 | 2 | 0 | 34 | 0
2 | District Office (Phone, Facs, Email, Post Internet etc) (7 Dist. x 36 months) | 252 |  | 0 | 0.64212 |  | 0 | 7 | 7 | 14 | 0 | 0 | 0 | 0.035673 | 14 | 0 | 238 | 0
| Sub Total B.VIII |  |  | 102600000 | 0.87145 | [5 empty] | 2850000 | 2850000 | 5700000 | 0.048414 |  | 5700000 |  | 96900000
B.VI | OFFICE EQUIPMENTS
1 | Provincial Office :
| a. Computer (rental) 2 unit/month | 72 |  | 0 | 0.42808 |  | 0 | 2 | 2 | 4 | 0 | 0 | 0 | 0.023782 | 4 | 0 | 68 | 0
| b. Printer (rental) 1unit/month | 36 |  | 0 | 0.10702 |  | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0.0059455 | 2 | 0 | 34 | 0
2 | District Office (7 Offices) :
| a. Computer (rental) 2 unit/district/month | 504 |  | 0 | 3.2106 |  | 0 | 7 | 7 | 14 | 0 | 0 | 0 | 0.089183 | 14 | 0 | 490 | 0
| b. Printer (rental) 1 unit/month | 252 |  | 0 | 0.74914 |  | 0 | 7 | 7 | 14 | 0 | 0 | 0 | 0.041619 | 14 | 0 | 238 | 0
| c. Digital Camera (rental) 1 unit/month/district | 252 |  | 0 | 0.42808 |  | 0 | 7 | 7 | 14 | 0 | 0 | 0 | 0.023782 | 14 | 0 | 238 | 0
| Sub Total B.VI |  |  | 579600000 | 4.9229 |  | 0 |  |  |  | 10850000 | 10850000 | 21700000 | 0.18431 |  | 21700000 |  | 557900000
B.VII | OFFICE COST
1 | Provincial Office :
| a. Office Supply | 36 |  | 0 | 0.12231 |  | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0.0067949 | 2 | 0 | 34 | 0
| b. Computer/Printer Supply | 36 |  | 0 | 0.12231 |  | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0.0067949 | 2 | 0 | 34 | 0
2 | District Office (7 Offices) :
| a. Office Supply | 252 |  | 0 | 0.85616 |  | 0 | 7 | 7 | 14 | 0 | 0 | 0 | 0.047564 | 14 | 0 | 238 | 0
| b. Computer/Printer Supply | 252 |  | 0 | 0.85616 |  | 0 | 7 | 7 | 14 | 0 | 0 | 0 | 0.047564 | 14 | 0 | 238 | 0
| c. Survey Equipments (7 X 12) | 84 |  | 0 | 0.35673 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 0
| Sub Total B.VII |  |  | 272400000 | 2.3137 |  | 0 |  |  |  | 6400000 | 6400000 | 12800000 | 0.10872 |  | 12800000 |  | 259600000
B.VIII | REPORTS
1 | Inception Report (15 copies)/district | 15 |  | 0 | 0.0063702 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0
2 | Monthly Report (15 copies/month)/district | 540 |  | 0 | 0.22933 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540 | 0
3 | Quarterly Report (15 copies/3 months)/district | 180 |  | 0 | 0.076443 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0
4 | Annual Report (15 copies/year)/district | 45 |  | 0 | 0.028666 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
5 | Special Report (5 copies/years)/district | 45 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
6 | Years Report | 45 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
7 | Draft Final Report (15 copies)/district | 15 |  | 0 | 0.01274 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0
8 | Prov. Gov ICR Report | 45 |  | 0 | 0.038221 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
9 | Final Report (15 copies)/district | 15 |  | 0 | 0.019111 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0
10 | MIS Input (5 copies)/6 month/district | 15 |  | 0 | 0.0063702 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0
| Sub Total B.IX |  |  | 49125000 | 0.41725 |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 |  | 49125000
B.IX | OFFICE RENTAL & FURNITURE AND O & M
1 | Province Office Rental (1 unit x 36 months) | 3 |  | 0 | 0.73385 |  | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0.48923 | 2 | 0 | 1 | 0
2 | District Office Rental (7 unit x 36 months) | 252 |  | 0 | 4.2808 |  | 0 | 168 |  | 168 | 0 | 0 | 0 | 2.8539 | 168 | 0 | 84 | 0
| Sub Total B.X |  |  | 590400000 | 5.0146 |  | 0 | 170 | 0 | 170 | 393600000 | 0 | 393600000 | 3.3431 | 170 | 393600000 | 85 | 196800000
| TOTAL REIMBURSABLE EXPENSES |  |  | 5048725000 | 42.882 |  | 0 |  |  |  | 482350000 | 85300000 | 567650000 | 4.8214 |  | 567650000 |  | 4481075000